## Sheet1
Application Name : Mail Client |  |  |  |  | UI Assigned | Backend Assigned
[5 empty] | Swayan, Himanshu, Sambedan | Amar, Chitta, Ranjita, Dibya
Sl No | Module | Feature | Sub Feature | Fields | UI In Days | Backend In Days | Start Date | End Date
| Admin | Department | Create,Update,Delete,Get, Get All, Filter, Pagination | Name | 4 | 7 | 20-01-2025 | 25-01-2025
|  | Roles | Create,Update,Delete,Get, Get All, Filter, Pagination | Name
|  | Users | Create,Update,Delete,Get, Get All, Filter, Pagination | Email, Password, Name, Role, Department, AuthId, Phone, ActiveStatus, Refresh Token, Refresh Token Expire On
|  | Category | Create,Update,Delete,Get, Get All, Filter, Pagination | UserId, Name, Icon, Color, AccountId, ParentId, Type, Rules,
| Identiry | Login | Login, Refresh Token, Logout, Reset Password | Email, Password, Refresh Token
| Mail | Mail UI | Inbox |  | 13 | 20 | 23-01-2025 | 2025-08-02
Compose and Scheduled Mail
Sent
Draft
DMS(Attachments)
|  | Mail List With Body | Get, Get All, Filter, Pagination |  | 2 | 3 | 2025-08-02 | 2025-12-02
|  | Folder Module | Custom folder |  | 2 | 5 | 2025-08-02 | 2025-12-02
|  | Calender | Event Calender |  | 2 | 3 | 2025-12-02 | 15-02-2025
|  | Template Creation |  |  | 2 | 3 | 2025-12-02 | 15-02-2025
|  | Search & Filter functionality |  |  | 2 | 3 | 17-02-2025 | 20-02-2025
|  | Account - add new mail server | Multipule mail configure |  | 2 | 2 | 18-02-2025 | 23-02-2025
|  | Activity Log | user activity log |  | 3 | 5 | 23-02-2025 | 28-02-2026
[5 empty] | 32 | 51